*DRILLING REPORT REFLECTS OPERATIONS AS OF 7:00 AM*

4/27/2020	0’ (0’) Moving in rig.

4/28/2020	0’ (0’) Rig up, prep to spud.

4/29/2020	342’ (342’) Drilling. Spudded at 10:00 p.m. on 4/28/20.

4/30/2020	1282’ (940’) Drilling. Deviation 1° at 545’. Deviation 0.25° at 859’.

5/1/2020	1745’ (463’) Tripping out of hole to run surface pipe. Deviation 0.75° at 1298’. Deviation 1.75° at 1745’.

5/2/2020	1745’ (0’) Tripping in hole to resume drilling. Set 8 5/8” casing at 1740’ with 650 sx 65/35 POZ tailed by 150 sx Class C cement. Circulated 100 bbl cement to surface.

5/3/2020	2022’ (277’) Drilling.

5/4/2020	2308’ (286’) Drilling. Deviation 1.5° at 2214’.

5/5/2020	2497’ (189’) Drilling.

5/6/2020	3065’ (568’) Drilling.

5/7/2020	3631’ (566’) Drilling.

5/8/2020	4210’ (579’) Drilling.

5/9/2020	4600’ (390’) Drilling. Deviation 0.75° at 4325’.

5/10/2020	4770’ (170’) Drilling.

5/11/2020	5028’ (258’) Drilling.

5/12/2020	5400’ (372’) Drilling.

5/13/2020	5662’ (262’) Drilling.

5/14/2020	5845’ (183’) Drilling. Deviation 1° at 5660’.

5/15/2020	5914’ (69’) Got circulation back, tripping in hole. Lost circulation at 5914’.

5/16/2020	5960’ (46’) Circulating to clean hole.

5/17/2020	6284’ (324’) Mixing mud and LCM, preparing to make a bit trip.

5/18/2020	6284’ (0’) Tripping in hole with new bit.

5/19/2020	6420’ (136’) Tripping in hole for DST #1.

DST #1 Granite 6370’-6420’

Rec: 45’ Mud

32-35/1835#, 40-44/1830#

5/20/2020	6490’ (70’) Drilling.

5/21/2020	6550’ (60’) Tripping out of hole with DST #2.

DST #2 Granite 6505’-6550’

Rec: 5’ Mud

30-26/1237#, 29-27/1487#

5/22/2020	6650’ (100’) Tripping out of hole to log.

5/23/2020	6650’ (0’) Logging well.

5/24/2020	6650’ (0’) Laying down drill pipe, preparing to run casing.

5/25/2020	6650’ (0’) Preparing to cement casing.

5/26/2020	6650’ (0’) Circulating between stages 1 and 2 of cement job.

5/27/2020	6650’ (0’) Rigged down, waiting to move. Rig released at 8:00 p.m. 5/26/20.

Ran 156 jts 5.5” 15.5# casing, set at 6619’. DV tools set at 4911’ and 3205’. Ran baskets at 5862’, 4957’, 4785’, 4701’, and 3247’. Ran 23 centralizers, 10 on bottom, 10 from 4911’ to 4027’, above and below both DV tools. Pipe stuck while running in casing, ran free point tool, determined free point at 2509’. Spotted 67 bbl oil and worked pipe free. Finished running in casing and circulated for 4 hours to recondition mud. Cemented 1st stage with 350 sx 50/50 poz. Plug landed, opened 1st DV tool and circulated for 6 hours. Did not circulate cement from 1st stage off bottom. Cemented 2nd stage with 175 sx 65/35 poz and tailed with 100 sx thixotropic. Plug landed, opened 2nd DV tool and circulated for 4 hours. Did see circulated cement from 2nd stage off bottom. Cemented 3rd stage with 450 sx 65/35 poz tailed with 50 sx thixotropic. Plug landed, did see cement circulated to pit. Cemented mouse hole and rat hole with 50 sx cement. 3rd stage plug landed at 3:30 p.m. 5/26/2020.

5/28/2020	Wait on completion.

6/22/20		Waiting on completion.

6/29/20		MIRU BX Rig #5.  TIH w/ 4-7/8” bit and 2-7/8”, 6.5# new API tubing.  Tag top DV @

3195’ KB tool and drill out.  Circulate hole clean.  TIH to bottom DV tool.  Tag bottom DV tool @ 4900’.  Started drilling bottom DV tool.  Circulate hole clean, pull 1 jt and shut down.

6/30/20		Drill out bottom DV tool and circulate hole clean.  Tag PBTD @ 6478’ KB (PBTD should to be @ 6535’ KB).  Circulate hole clean.  TOH w/ tubing and bit.  Ran CBL- PBTD @ 6480’ KB.  Top of cement bottom stage @ 5027’ KB, but cement from top stage appears to begin @ 4976’ KB (DV @ 4911’ KB).  Good bond across bottom stage where cement present.  Top of cement, middle stage @ DV tool @ 3204’, but poor bond from 3505’-3231’ KB.  Good bond across potential pay zones.  TOC, top stage above fluid level @ 135’, but poor bond from 1990’-213’.  Pressure test casing to 1900#- held.  SIH w/ 4-7/8” bit, 5-1/2” casing scraper and 2-7/8” to drill out more rat hole.  Shut down.

7/1/20		Tag top of cement @ 6478’ KB.  Started drilling cement.  Drilled down to 6538’ KB and started recovering rubber and metal.  Pull up and start swabbing casing fluid level down.  Shut down.

7/2/20		Swab casing fluid level down to 5300’.  Shut down.

7/3/20		Shut down for holiday.

7/4-5/20	Shut down.

7/6/20		Perforate Granite from 6510’-6525’ KB, 4 SPF.  Tagged TD @ 6533’ KB with perforating gun.  TIH w/ Model R PKR, SN and 2-7/8” tubing.  Set PKR @ 6479’ KB.  Ran swab- fluid level 5100’ from surface.  Recovered 8 BW on swab down at 4:00.  Next run dry.  Waited 30 minutes between pulls:

5:00	2 BW

5:30	1 BW

Shut down.

7/7/20		SITP- 0#- light blow on tubing.  Ran swab- fluid level 3900’ from surface, 100% water.  Recovered 13 BW on swab down at 9:00.  Next run- 20’ water.  Recovered 8 BW in 3 hours of swabbing.  Treat well with 1000 gallons 7% HCL/5% HFG-626 (HF acid substitute).  Started feeding 0.5 BPM @ 1200# after hole loaded.  Increased rate to 1 BPM and pressure dropped to 0#.  Treated 1 BPM @ 0#.  ISIP- vacuum.  TLTR 64 BBL.  Started swabbing at 1:30- fluid level 500’ from surface.

2:30	33 BW, fluid level 3900’ from surface

3:30	24 BW.  Started swabbing from SN at end of hour.  Fluid level 5900’ from surface.

4:30	17 BW- fluid level staying 5900’ from surface.  Recovered remainder of load.

5:30	20 BW- fluid level 6100’ from surface.

Shut down.  Will perform step-rate test in morning.

7/8/20		SITP-0#, light blow on tubing.  Ran swab- fluid level 2300’ from surface- recovered 100% water.