*DRILLING REPORT REFLECTS OPERATIONS AS OF 7:00 AM*

3/6/20	Moving in rig.

3/7/20	40’ (40’) Drilling. Spudded at 11:00 pm on 3/6/20.

3/8/20	505’ (465’) Drilling. Deviation 0.5° at 278’.

3/9/20	1340’ (835’) Drilling.

3/10/20	1770’ (430’) Finishing cementing surface casing. Set 8 5/8” casing at 1763’ with 650 sx 65/35 POZ tailed by 150 sx Class C cement. Circulated 30 bbl cement to surface. Deviation 0.75° at 1770’.

3/11/20	1935’ (165’) Drilling.

3/12/20	2290’ (355’) Reaming/drilling.

3/13/20	2400’ (110’) Drilling.

3/14/20	2453’ (53’) Drilling.  Deviation 3/4°

3/15/20	2610’ (157’) Drilling.

3/16/20	2991’ (381’) Drilling.

3/17/20	3446’ (455’) Drilling.

3/18/20	3939’ (493’) Drilling.

3/19/20	4335’ (396’) Drilling. Deviation 0.75° at 3945’.

3/20/20	4615’ (280’) Circulating hole clean at core point.  Will do short trip and come out of hole and prep to start coring.

3/21/20	4615’ (0’) Reaming with core barrel.

3/22/20	4622’ (7’) Coring.  Started coring at 4615’.

3/23/20	4683’ (61’) Coring. Recovered complete core #1 from 4615’ – 4676’.

3/24/20	4769’ (86’) Coring. Recovered complete core #2 from 4676’ – 4736’.

3/25/20	4880’ (111’) Preparing to start coring. Recovered complete core #3 from 4736’ – 4796’. Deviation 0.25° at 4880’.

3/26/20	4934’ (54’) Coring. Recovered partial core #4 from 4880’ – 4897’.

3/27/20	5109’ (175’) Drilling. Recovered complete core #5 from 4897’ – 4957’.

3/28/20	5380’ (271’) Waiting on new bit, preparing to ream.

3/29/20	5380’ (0’) Preparing to core.

3/30/20	5439’ (59’) Tripping in hole for DST #1. Recovered complete core #6 from 5380’ – 5439’.

3/31/20	5439’ (0’) Tripping in hole to resume drilling. Tried to run DST #1 but hit a bridge at 2046’.

DST #2 Lower Mississippian 5379’ – 5439’

Rec: 40’ mud

36-41/1376#, 41-50/1374#

4/1/20	5640’ (201’) Tripping in hole to core #7. Deviation 1° at 5640’.

4/2/20	5719’ (79’) Tripping out of hole with core #8. Recovered partial core #7 from 5640’ – 5670’. Recovered partial core #8 from 5670’ – 5719’.

4/3/20	5780’ (61’) Tripping out of hole, preparing to core.

DST #3 Viola 5640’ – 5710’

Rec: 300’ mud cut water (5% mud, 95% water)

52-115/1477#, 104-164/1474#

4/4/20	5814’ (34’) Coring. Recovered partial core #9 from 5780’ – 5811’.

4/5/20	5826’ (12’) Letting LCM pill set. Recovered partial core #10 from 5811’ – 5826’. Lost circulation at 5826’. Recovered full returns, went in with conventional bit and then lost returns. Mixed LCM pill to displace out of pipe and let set.

4/6/20	5850’ (24’) Tripping out of hole with core tool. Resumed drilling conventional from 5826’ to 5850’. Attempted to core at 5850’ but lost circulation again. Did not continue coring.

4/7/20	5865’ (15’) Drilling with conventional bit.  Regained circulation and resumed drilling with conventional bit.

4/8/20	5959’ (94’) Reaming to prepare for next core #11.

4/9/20	6019’ (60’) Tripping in hole for next core #12. Recovered complete core #11 from 5,959’ – 6,019’.

4/10/20	6069’ (50’) Coring core #13. Recovered partial core #12 from 6,019’ – 6,042’.

4/11/20	6125’ (56’) Coring core #14. Recovered complete core #13 from 6,042’ – 6,102’.

4/12/20	6210’ (85’) Coring core #15. Recovered complete core #14 from 6,102’ – 6,162’.

4/13/20	6273’ (63’) Tripping out of hole with core #16. Recovered complete core #15 from 6,162’ – 6,222’. Recovered partial core #16 from 6,222’ – 6,273’.  Core bit quit drilling with 51’ of recovery at 6273’.

4/14/20	6278’ (5’) Preparing to trip in hole with coring tool at 6278’ with diamond coring bit for core #17.  In prior 24 hrs ran core bbl and attempted to resume coring @ 6,274’ and could not make hole.  Pulled core bit and had 3” of gray feldspar in core bbl.  Drilled conventional from 6,273’ – 6,278’ to get past hard spot.  Sample descriptions from 6273-6278 were pink granite (feldspar).  It appears Reagan sand is eroded and gone and we are now in solid granite.  Plan to try coring again with diamond core bit to confirm.

4/15/20	6285’ (7’) Coring core #17.  Coring at 1 ft/hr so very slow coring.  Likely we are coring hard, solid granite.

4/16/20	6300’ (15’) Tripping out of hole with core #17. Recovered partial core #17 from 6,278’ – 6,300’.  This completes coring.  Plan to cut to TD of 6500’ and run logs.

4/17/20	6379’ (79’) Drilling ahead.

4/18/20	6500’ (121’) Drilling ahead.

4/19/20	6550’ (50’) Logging first run. Deviation 2° at 6,550’.

4/20/20	6550’ (0’) Logging.  RTD is 6550’. LTD is 6554’.

| Core | Interval | Feet Cored |
| --- | --- | --- |
| Core #1 | 4615’ – 4676’ | 61’ |
| Core #2 | 4676’ – 4736’ | 60’ |
| Core #3 | 4736’ – 4796’ | 60’ |
| Core #4 | 4880’ – 4897’ | 17’ |
| Core #5 | 4897’ – 4957’ | 60’ |
| Core #6 | 5380’ – 5439’ | 59’ |
| Core #7 | 5640’ – 5670’ | 30’ |
| Core #8 | 5670’ – 5719’ | 49’ |
| Core #9 | 5780’ – 5811’ | 31’ |
| Core #10 | 5811’ – 5826’ | 15’ |
| Core #11 | 5959’ – 6019’ | 60’ |
| Core #12 | 6,019’ – 6,042’ | 23’ |
| Core #13 | 6,042’ – 6,102’ | 60’ |
| Core #14 | 6,102’ – 6,162’ | 60’ |
| Core #15 | 6,162’ – 6,222’ | 60’ |
| Core #16 | 6,222’ – 6,273’ | 51’ |
| Core #17 | 6,278’ – 6,300’ | 22’ |
| Total Feet Cored To Date: |  | 778’ |